## Backlog - Open
Travel Sentiment Product Backlog
Colleen Dunlap
PBI | Agile State | Priority | Est. Story Pts | Importance | Date Added | Notes | Story
Create Twitter Developer Account | Sprint | 1 | 1 | High | 2019-01-12 | To access Twitter API | Application will use Twitter to help users either decide where they want to travel or to engage with a location before they travel
SPIKE: Find Usable Boiler Plate | Sprint | 2 | 3 | High | 2019-01-12 | Why reinvent the wheel? | Web application. Node or Python probably.
Pull Trends Geographically | Icebox | 3 | 5 | Medium | 2019-01-12 | Medium Importance because uncertainty whether MVP will involve finding a place to travel or learning about an already decided place to travel | User wants to know what's happening in the place they're about to travel to. So they hop on our travel sentiment application and search for trending topics in the area.
Get Locations with Trending Topics | Icebox | 4 | 5 | Medium | 2019-01-12 | See above | User wants to find a place to travel to with an up and coming music scene. Specifically EDM. So they hop on our travel sentiment app and look for locations that have music as a trending topic. The obvious ones come up--Seattle, LA, Barcelona… but then they see a cute quirky town in Malta with a TON of festivals coming up. Sounds exciting!

## Glossary
PBI: | Must be things that are added for customer value
EBI: | Efficiencies that need are used for long-run efficiencies, but do not add direct customer value
SBI: | Sprint item which is a sub componenet of each PBI
Acceptance Criteria: | Criteria by which the PBI and SBI are considered done
Story Pts: | 1,2,3,5,8,13,20,40,100,∞
Time
Effort
Difficulty